## Fully Implemented
# | Feature | Details
1 | User Registration | Form with email uniqueness check, JWT-based login, localStorage session
2 | User Login / Logout | JWT token generation, role-based redirect (admin / user)
3 | Admin Route Guards | AdminGuard, UserGuard protecting role-specific routes
4 | HTTP Interceptor | Attaches Bearer token to all outgoing requests automatically
5 | Admin: Add Donor | Form with full donor details — name, blood group, units, city, date
6 | User: Self-register as Donor | Same form via /addAsDonor endpoint; redirects to user dashboard
7 | Donor List with Search | Client-side filter by blood group (case-insensitive regex)
8 | Blood Inventory View | Aggregated by group — donor count + total units per blood type
9 | User: Request Blood | Form capturing disease, units, contact info; persisted with status
10 | Admin: View All Requests | Table listing all blood requests with accept / reject action buttons
11 | User: View Own Request History | Filtered by email, displays current status of each request
12 | User Dashboard Stats | Total donors, users, blood groups, units, personal donation & request count
13 | Admin Dashboard | Blood stock summary table with live inventory from DB
14 | User Profile View & Edit | Fetch, edit, and save name, mobile, blood group, age, password
15 | Admin: View All Users | Full user list accessible from admin dashboard
16 | Auto-expiry of Blood Samples | Samples older than 90 days auto-deleted on every inventory API call

## Half Implemented
# | Feature | What Works | What's Missing / Broken
1 | Admin Login | Hardcoded check in frontend (admin@gmail.com / admin123) | No admin in DB; bypasses JWT; no backend admin authentication
2 | Accept / Reject Blood Request | Status updated in database | Updates ALL requests for an email — not a specific request (no ID-based query)
3 | User Donation Count | Endpoint exists, frontend calls it | Hardcoded 'if name == gowtham' — only works for one hard-coded person
4 | Auth Guard | File exists and is wired to routes | canActivate() always returns true — provides zero protection
5 | User Profile Fetch | getProfileDetails() is called on init | Subscription block is commented out — data never renders
6 | Request Blood Error Handling | Success flow and redirect work | On error, silently redirects — user sees no error message
7 | Blood Stock Deduction on Approval | Request status is accepted in DB | Inventory units are NOT reduced when a request is approved
8 | Role-based Route Protection | Guards exist on some routes | donorlist, bloodStock, bloodStockuser have NO guards — publicly accessible

## Not Implemented
# | Feature | Priority | Notes
1 | Password Hashing | Critical | NoOpPasswordEncoder — passwords stored as plain text
2 | Password Reset / Forgot Password | High | No endpoint or UI exists anywhere in the project
3 | Email Notifications | High | No emails on request approval, registration, or blood expiry
4 | Inventory Deduction on Approval | High | Accepting a request does not reduce available unit count
5 | Donor Eligibility Validation | Medium | No checks for age limits, donation frequency, or health criteria
6 | Pagination on Lists | Medium | All donor/user/request lists load unlimited records from DB
7 | Export Reports (CSV / PDF) | Medium | No data export functionality of any kind
8 | Blood Compatibility Matching | Medium | No O- universal donor logic, no Rh factor differentiation
9 | JWT Refresh Token | Medium | Tokens expire in 10 h with no refresh mechanism
10 | 404 / Catch-all Route | Low | Unknown URLs render a blank page — no redirect or error page
11 | Audit Log for Admin Actions | Low | No record of who accepted/rejected which request or when
12 | Loading / Spinner States | Low | No spinners or skeleton screens during API calls
13 | Form Validation Feedback | Low | Validation is HTML-only; no custom error messages shown to user

## Critical Bugs
# | Bug Description | Location / File | Impact
1 | Donation count only works for user named 'gowtham' | DonorController.java : line 203 | Feature broken for all other users
2 | Accept/reject updates ALL requests for an email, not one | RequestingBloodRepository.java — no ID in SQL query | Data integrity — wrong requests change status
3 | Expired blood deletion uses donor name not ID | DonorRepository.java : deleteByUsername() | Can delete wrong records if two donors share a name
4 | Admin credentials hardcoded in frontend source code | registration.service.ts : adminLoginFromRemote() | Security — credentials visible to anyone viewing JS bundle
5 | State-changing operations use GET instead of POST/PUT | /acceptstatus/{email}, /rejectstatus/{email} | Unsafe — browser prefetch or link preview can trigger actions